## Sheet1
openHPI - MOOC Pre-Planning Tool
Course title
Responsible Professor
Course administrators (HPI addresses)
Course moderators (HPI addresses)
Course teachers (HPI addresses)
Helpdesk
Access to MOOC planner and quiz sheets (gmail addresses if available)
URL
Quiz Template
MOOC Planner
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Start Dates (Week 1 - x) |  | 0 | 1900-01-06 | 1900-01-13 | 1900-01-20 | 1900-01-27 | 1900-02-03 | 1900-02-10 | 1900-02-17
Course Announcements (Min. 1 per week, additional announcements if required) |  | 0 | 1900-01-06 | 1900-01-13 | 1900-01-20 | 1900-01-27 | 1900-02-03 | 1900-02-10 | 1900-02-17
Deadlines Weekly Assignments |  | 1900-01-13 | 1900-01-13 | 1900-01-20 | 1900-01-27 | 1900-02-03 | 1900-02-10 | 1900-02-17 | 1900-02-24
| Deadlines | 0: NOTES
Course Start |  | 0: All other dates are calculated automatically.
Trailer |  | 0: The trailer should be available before the first global course announcement (4 weeks before the course starts)
Global Course Announcement I |  | 0: First dedicated global announcement (4 weeks before course start)
Global Course Announcement II |  | 0: Second dedicated global announcement (1 week before course start)
German: Transcripts (Agency) |  | 0: German courses, are transcripted manually by an agency. This takes some time and requires video recordings to be done early (about 8 weeks in advance).
German: Transcripts/Slides (Powerpoint) |  | 0: We provide automatedly generated English subtitles and slides for courses in German language. We use the tool DeepL for this purpose. To be able to do this in time, we need the Powerpoint slides and the transcripts from the agency.
English: Auto-generated transcripts + QA (by course team) |  | 0: Generally, we're working with Politrans, a tool provided by the University of Valencia, to automatically generate transcripts. These transcripts are very raw. Upper-case/lower-case and punctuation have to be added. The auto-generated text needs to be QA'd by the teaching team (workload estimate: 1h per 10 min. video). Credentials to access the translation tool are available on request.
Texts and Course Visual |  | 0: Course abstract, course description, module descriptions, course registration email, target group definition
Selftests: 3 questions |  | 0: Please use the Quiz tool to create quizzes and import them. Advantages: Reusability
Weekly Exams: 15 questions |  | 0: Please use the Quiz tool to create quizzes and import them. Advantages: Reusability
Additional Learning Material |  | 0: Video items allow to add additional material. Further additional material can be provided for download in text items. Slide previews, downloadable video, and audio-only files are generated automatically.
Slides(PDF) |  | 0: Powerpoint slides can (and should) be added to video items. There is a high demand from the users for the downloadable slides.
Peer Assessment Planung/ Beratung |  | 0: If you're interested to provide more complex tasks than just MC/MA-quizzes, please contact thomas.staubitz@hpi.de